Project Plan

Qualit AI — AI Quality Co-Pilot

Version 1.0

October 2026

Status: Draft

# 1. Document Control

| Field | Detail |
| --- | --- |
| Document Title | Qualit AI — Project Plan and Implementation Roadmap |
| Version | 1.0 |
| Date | October 2026 |
| Status | Draft |
| Author | Project Management / Engineering Team |
| Audience | Sponsors, Project Team, Stakeholders |

## Revision History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Oct 2026 | Project Team | Initial project plan |

# 2. Project Overview

This plan describes how to build Qualit AI from scratch: an AI quality co-pilot for Agile QA teams. The project delivers a web platform (Angular client + FastAPI backend + MongoDB) covering analytics, risk prediction, bug triage, GenAI test generation, coverage analysis, release readiness, codeless API testing and accessibility scanning, with Azure DevOps/Jira integrations and hybrid (offline-capable) AI engines.

Primary deliverables:

- Production-ready source code in an Nx monorepo (apps/client, apps/api) with automated tests and CI.

- Deployable artifacts: Docker images, Docker Compose stack, Kubernetes manifests.

- Complete documentation set: BRD, FRD, SRS, System Design, Test Plan, user walkthrough and API guidelines.

- Pilot-ready environment seeded with demo data and four role-based demo accounts.

# 3. Methodology

- Agile/Scrum with two-week sprints and a working demo at the end of each sprint.

- Trunk-based development on main with pull requests and CI-required checks.

- Vertical feature slicing: each sprint delivers end-to-end capability (UI → API → data).

- Definition of Done: code reviewed, tests green in CI, documentation updated, deployed to staging.

# 4. Project Organization

| Role | Responsibilities | Allocation |
| --- | --- | --- |
| Executive Sponsor | Vision, budget, unblocking cross-team issues | Part-time |
| Product Owner / BA | Backlog, FRD/BRD ownership, UAT acceptance | Full-time |
| Project Manager | Plan, status, risks, stakeholder communication | Part-time |
| Technical Lead / Architect | Architecture, design reviews, ML approach, API contracts | Full-time |
| Backend Developers (2) | FastAPI services, ML engines, connectors, jobs | Full-time |
| Frontend Developer (1) | Angular dashboard, charts, job UX | Full-time |
| QA Engineer (1) | Test plan, automation (pytest), UAT coordination | Full-time |
| DevOps (0.5) | CI/CD, Docker/Kubernetes, environments | Part-time |

# 5. Phases and Milestones

Six phases over approximately 21 weeks (≈ 5 months):

| Phase | Duration | Key Activities | Exit Deliverable |
| --- | --- | --- | --- |
| P0 — Foundation | Weeks 1–2 | Nx monorepo, CI pipelines, Docker/K8s skeleton, MongoDB, JWT auth, RBAC, tenancy, seed/migration | Secure login with four roles on deployed staging |
| P1 — Data & Analytics | Weeks 3–6 | ADO/Jira connectors, CSV ingestion, mock generator, analytics dashboard, module risks, caching | Dashboard live with real and mock data |
| P2 — Predictive Quality | Weeks 7–10 | Risk scoring, RBT plans, triage (duplicates + prediction), flaky analysis, model training pipeline | Triage console and RBT plan used by QA pilot users |
| P3 — GenAI Test Engineering | Weeks 11–15 | Functional test generation, execution recording/analysis, coverage gap, release readiness | Requirements-to-ZIP generation and coverage reports |
| P4 — Test Execution Tooling | Weeks 16–18 | Codeless API testing (Excel engine), accessibility scanning, documents API | API and accessibility reports downloadable |
| P5 — Hardening & Release | Weeks 19–21 | Performance passes, security review, UAT, docs finalization, release packaging | UAT sign-off, v1.0 release |

## Milestones

| ID | Milestone | Target |
| --- | --- | --- |
| M1 | Foundation complete (auth, RBAC, CI, deployment skeleton) | End of Week 2 |
| M2 | Data platform and analytics dashboard operational | End of Week 6 |
| M3 | Risk, RBT and triage features demo-ready | End of Week 10 |
| M4 | GenAI test generation and coverage analysis demo-ready | End of Week 15 |
| M5 | API testing and accessibility scanning complete | End of Week 18 |
| M6 | UAT sign-off and v1.0 release | End of Week 21 |

# 6. Timeline

Gantt overview (■ = active phase):

| Phase | W1-2 | W3-6 | W7-10 | W11-15 | W16-18 | W19-21 |
| --- | --- | --- | --- | --- | --- | --- |
| P0 Foundation | ■ |  |  |  |  |  |
| P1 Data & Analytics |  | ■ |  |  |  |  |
| P2 Predictive Quality |  |  | ■ |  |  |  |
| P3 GenAI Test Engineering |  |  |  | ■ |  |  |
| P4 Test Execution Tooling |  |  |  |  | ■ |  |
| P5 Hardening & Release |  |  |  |  |  | ■ |
| Documentation (continuous) | ■ | ■ | ■ | ■ | ■ | ■ |
| CI/CD & QA (continuous) | ■ | ■ | ■ | ■ | ■ | ■ |

# 7. Work Breakdown Structure

| Epic | Scope Summary | Phase |
| --- | --- | --- |
| Platform foundation | Monorepo, CI, Docker/K8s, health probes, env config | P0 |
| Identity & access | Login, JWT, bcrypt, RBAC (4 roles, 13 permissions), user admin | P0 |
| Data ingestion | ADO/Jira connectors, CSV uploads, mock dataset generator, seeding | P1 |
| Analytics dashboard | Sprint metrics, defect trends, charts, caching, refresh | P1 |
| Risk analytics | Task risk scores, heatmap, rationale | P2 |
| RBT planning | Plan generation (LLM/rules), test cases, settings | P2 |
| Bug triage | Duplicate detection, label prediction, rationale, submission | P2 |
| Flaky analysis | Analyzer with cached LLM results | P2 |
| Functional test gen | Doc upload, manifest, Cucumber/Playwright generation, traceability, ZIP | P3 |
| Execution recording | Report parsing (5 formats), ALM import, AI analysis | P3 |
| Coverage gap | Requirement extraction, scoring, gap recommendations | P3 |
| Release readiness | Snapshot aggregation, confidence score | P3 |
| Codeless API testing | Excel engine, variable chaining, HTML report | P4 |
| Accessibility | Playwright + axe-core + Lighthouse, auth modes, reports | P4 |
| Documents | Upload/download/delete API with validation | P4 |
| Job framework | progress_tracker, cancel_manager, SSE, download endpoints | P1–P4 (as needed; core in P0/P1) |
| Hardening | Performance, security review, UAT, final docs | P5 |

# 8. Risks

| ID | Risk | P | I | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | LLM output quality below expectations | M | H | Hybrid fallback, prompt iteration, golden-sample evaluation in test plan | Tech Lead |
| R2 | External ALM API changes or access delays | M | M | Connector isolation, query-safety tests, CSV upload path | Backend |
| R3 | Key personnel availability | L | H | Cross-training, documented architecture, paired reviews | PM |
| R4 | Scope creep from placeholder features | M | M | Change control; UI/UX testing deferred by agreement | PO |
| R5 | Sensitive credentials in config | L | H | Env-only secrets, least-privilege RBAC, security review in P5 | DevOps |
| R6 | ML prediction accuracy weak on customer data | M | M | Confidence scores surfaced; threshold tuning; data quality validation | Tech Lead |
| R7 | Integration test flakiness (browser scans) | M | L | Retries, stable demo targets, MOCK data for CI | QA |

# 9. Quality Gates

- Pull requests require one approval and green CI (lint + tests).

- pytest suite must pass on every change: npm run test:api (uv run pytest apps/api/tests -v).

- Client build must pass: npm run build:client.

- Each phase exit requires a demo against acceptance criteria from the FRD.

- Security review and performance smoke tests gate the P5 release.

- UAT sign-off by Product Owner and QA Lead required before v1.0 tagging.

# 10. Communication Plan

| Ceremony / Artifact | Cadence | Audience |
| --- | --- | --- |
| Daily standup | Daily, 15 min | Project team |
| Sprint planning | Every 2 weeks | Team + PO |
| Sprint review/demo | Every 2 weeks | Team + stakeholders |
| Status report | Weekly | Sponsor + stakeholders |
| Risk review | Weekly | PM + Tech Lead |
| Release notes | Per release | All |

# 11. Change Control

- Scope changes are logged as change requests with impact analysis (schedule, cost, quality) and approved by the Product Owner and Sponsor for material impacts.

- Requirement changes update the FRD/SRS with a new revision entry before implementation begins.

- Architecture decisions are recorded in design documents and reviewed by the Technical Lead.